## Slide 1: Failure-Aware Change Management Framework
Detecting, Controlling, and Correcting Failure Before It Scales MKD

## Slide 2: Failure-Aware Change Management Framework

## Slide 3: Detecting, Controlling, and Correcting Failure Before It Scales
A practical control framework for Healthcare IT change
Built for clinical workflow, data integrity, and operational continuity
Designed for early detection before harm spreads
Notes: This presentation introduces the Failure-Aware Change Management Framework for Healthcare IT professionals. The message is simple: In clinical environments, change management must catch failure early, contain it quickly, and fix it before it damages workflow, data quality, operations, or trust.

## Slide 4: Clinical Failure Signals
DICOM send succeeds, but ED clinicians report missing CT images
HL7 interface is green, but clinical meaning is wrong
Training completion is high, but workarounds spread by shift
Clinical champion attends meetings, then stops defending the change
Silence is mistaken for stability
Notes: This is what failure often looks like in Healthcare IT. The interface looks healthy. The dashboard is green. The plan says the next department is ready. But on the floor, clinicians may already be using phone calls, paper notes, duplicate checks, and side conversations to keep care moving. By the time the problem becomes obvious, the patient-safety risk may already be inside the workflow.

## Slide 5: Core Statement
Change Management is Failure Management.
Core Statement: Change management identifies failure early, controls the failure path, and implements corrective action before harm spreads.
Notes: The Core Statement is the anchor for the framework. Change management is not just communication, training, and adoption tracking. In a clinical setting, change management is failure management. It looks for early warning signs, limits exposure, and pushes the team to act before the problem spreads across people, process, technology, and trust.

## Slide 6: Foundational Reframe
Traditional View | Control-Oriented View
Adoption is achievable | Failure is the default
Resistance is the exception | Success is engineered
Plans hold with communication | Plans are tested by reality
Status reporting detects trouble | Control must be engineered
Notes: Many change plans start with optimism: Communicate well, train people, monitor progress, and adoption should follow. That is not enough in a hospital. Real change touches clinical judgment, unit routines, orders, results, handoffs, identities, and informal work. Expecting failure is not negative thinking. It is how serious teams protect care while they change the system.

## Slide 7: The Skipped Planning Question
Question: How will we know something is going wrong before it becomes a crisis?
It makes optimism accountable
It forces evidence before the post-mortem
It assigns control owners before failure becomes political
It turns discomfort into executable discipline
Notes: This is the question teams often skip because it tests the plan before reality does. The answer should not be a vague note in a risk register. It should name the warning signal, the owner, the threshold, the decision authority, and the fallback path before go-live pressure begins. If the team cannot answer this question, it is not managing failure. It is waiting for failure to show up on its own.

## Slide 8: Six Governing Principles
Failure Is the Default Condition of Change
Detection Must Be Actively Designed
Control Comes Before Scale
Failure Must Trigger Intervention
Corrective Action Must Be Implemented
Accountability Must Cross People, Process, and Technology
Notes: These six Governing Principles turn the Core Statement into daily management behavior. Expect failure. Design the way you will detect it. Control exposure before you expand the rollout. Treat warning signs as triggers for action, not material for a lesson-learned meeting months later. Then look across people, process, and technology because real failures rarely stay inside one workstream.

## Slide 9: From Risk Register to Intervention Design
Weak Artifact | Strong Control Design
Risk listed | Signal defined
Owner named | Owner authorized
Mitigation noted | Trigger threshold set
Escalation documented | Decision rights confirmed
Review scheduled | Intervention cadence active
Notes: The shift here is from documenting risk to planning the response. A risk register can be clean and still be useless if nobody knows which signal triggers which decision. The framework forces the implementation plan to become more concrete: Prevention, detection, response, ownership, and escalation thresholds all have to become part of the actual work.

## Slide 10: Applying the Framework
Map the People-Process-Technology domain and integrator risk.
Ask the six control questions for each material change element.
Convert answers into the Project Implementation Plan.
Govern execution through the dashboard, register, and decision log.
Notes: This is the practical sequence. First, map where failure can start. Then ask the six control questions for each important part of the change. Turn the answers into updates to the implementation plan. Finally, manage the work through the dashboard, register, and decision log. If this does not change the workplan, meeting rhythm, owner authority, or fallback path, then the team has talked about risk but has not created control.

## Slide 11: People-Process-Technology Overlay
Domain | Primary Failure Question
Technology | Does the system support safe clinical work?
Process | Does the workflow survive real conditions?
People | Are alignment and behavior real?
Integrator | Who controls cross-domain failure?
Notes: The People-Process-Technology overlay helps the team locate where failure can begin. Technology comes first because it is usually the easiest to inspect. Process comes next because workflow reality is often underestimated. People comes next because behavior changes by role, shift, influence, and pressure. The integrator layer matters because these areas cannot be managed as separate excuses.

## Slide 12: Six Control Questions
Diagnostic Area | Operating Question
Success Criteria | What does safe success look like?
Assumptions | What must be true for this to work?
Expected Failure | Where do we expect failure to appear?
Detection | How will we know the signal is credible?
Prevention | What must we do now to reduce exposure?
Control Response | What action do we execute when it appears?
Notes: Use these six questions at the project, workstream, unit, workflow, interface, role, and system-function level. The first three questions clarify what success means and where the weak points are. The last three questions define how the team will prevent, detect, and respond. If the answers do not change the implementation plan, the team has only discussed risk. It has not managed failure.

## Slide 13: Radiology Workflow Example
Area | Control Answer
Success Criteria | Orders, images, and reports move safely across RIS, PACS, and EHR
Assumptions | Orders, worklists, accession numbers, images, and reports stay synchronized
Expected Failure | Wrong exam context, missing images, delayed reads, or report delivery gaps
Detection | Worklist mismatches, unsigned backlog, PACS complaints, missing-result calls
Prevention | Validate ORM, DICOM Modality Worklist, routing, accession mapping, and reports
Control Response | Pause expansion, reconcile studies, fix mappings, activate manual escalation
Notes: Radiology is a useful example because it exposes the whole chain. Success is not just that the interface is live or that an image opens. Success means the right exam is ordered, scheduled, performed, read, signed, and delivered into the right clinical context. If worklist mismatches or missing-image complaints rise, the answer is not generic retraining. The answer is a controlled intervention.

## Slide 14: Technology Failure
Core Risk: The tool works technically but fails operationally
Interface transport can succeed while clinical meaning fails
Green dashboards can hide semantic failure
Wrong information creates patient-safety risk
Detection must combine logs, users, workflow, and data validation
Notes: Technology failure is not only downtime. An HL7 ACK, a successful DICOM send, or a normal vendor dashboard proves that something moved. It does not prove that the clinical meaning is correct. One of the highest-risk failures is wrong information moving through a system that appears healthy. That is why detection has to combine logs, user reports, workflow observation, and data validation.

## Slide 15: Process Failure
Core Risk: Designed workflow does not match real work
Current-State Error: The future state is built on a false baseline
Shadow Workflow: Workarounds expose missing steps or unsafe timing
Stuck Between Old and New: Hybrid operations become permanent
Control Task: Classify, control, and redesign broken workflow
Notes: Process failure happens when the design on the wall does not match the work on the unit. Shift patterns, handoffs, interruptions, walking distance, and informal coordination are not side issues. They are the work. A workaround is a signal. Sometimes it is unsafe behavior. Sometimes it is staff compensating for a bad design. The task is to classify it, control it, and redesign before the workaround becomes the normal way of operating.

## Slide 16: People Failure
Core Risk: Superficial agreement is mistaken for adoption
Attendance proves exposure, not competence
Quiet champions are a political signal
Influential Opponent: Informal authority works against change
Owner in Name Only: Accountability exists only on paper
Workarounds reveal the truth first
Notes: People failure is the gap between formal agreement and actual behavior. In clinical environments, adoption is proven under pressure: Busy shifts, handoffs, interruptions, and exception cases. Senior physicians, charge nurses, unit managers, analysts, and the unofficial problem solvers can make or break adoption even if they are not prominent on the project chart. When a champion goes quiet, treat it as evidence.

## Slide 17: The Integrator Layer
Real breakdown is controlled between domains
Technology defects get mislabeled as adoption problems
Process gaps get patched with manual work
People resistance exposes workflow flaws
Clean interfaces can still create unsafe behavior when workflow meaning fails
Notes: The integrator layer exists because serious failures move across domains. A technical defect can be blamed on users. A process defect can be hidden by manual cleanup. People resistance can expose a workflow flaw that leadership did not want to confront. If nobody owns the whole picture, the organization may solve the wrong problem very efficiently while the real failure path stays in place.

## Slide 18: Failure Management Dashboard
Layer | Purpose
Executive Snapshot | Force current leadership decisions
Failure Register | Track signal, control action, owner, and status
Decision Log | Record stop, change, accept, and defer choices
Review Cadence | Match frequency to clinical and operational risk
Notes: The dashboard is not a status report. A status report tells leaders what happened or what percent is complete. A failure management dashboard tells leaders what needs control now. If it does not force a decision to stop, change, accept, defer, or implement, then it is not really governing the implementation.

## Slide 19: Example Failure Register Entry
Field | Example
Failure Signal | DICOM send success with rising missing-image complaints
Scope | ED night shift, CT studies, PACS viewer and EHR imaging link
Threshold | More than 3 verified complaints in 4 hours
Control Owner | PACS administrator and ED clinical operations lead
Decision Required | Hold expansion, reconcile studies, validate routing, activate manual image access
Notes: This is the level of detail that makes the register useful. The signal is clear. The scope is bounded. The threshold is explicit. The owner pairing keeps technical and clinical operations in the same decision loop. At that point, the register becomes a control tool, not a parking lot for issues.

## Slide 20: Key Takeaways
Change management is failure management
Green systems can still create unsafe clinical work
Detection must be designed before go-live pressure arrives
Failure signals must trigger intervention, not later explanation
Control belongs across people, process, technology, and the integrator layer
Notes: The message is simple. Do not confuse silence with stability. Do not confuse availability with safety. Do not confuse compliance with adoption. This framework gives leaders a practical way to catch early warning signs, control exposure, and take corrective action before failure spreads through clinical workflow.

## Slide 21: Apply It to One Active Initiative
Discussion Prompt: Where is your current change portfolio confusing silence with stability?
Next Step: Select one initiative and build its control dashboard
Immediate Work: Define signals, owners, thresholds, and fallback paths
Operating Standard: Protect continuity, safety, trust, and decision quality
Notes: Start with one active initiative. Pick the project where silence is most likely being mistaken for stability. Build the dashboard. Define the signals. Authorize the owners. Set the thresholds. Decide what intervention happens when evidence appears. Compliance is not adoption. Availability is not operational success. Control the failure path before it controls the implementation.